## Sheet1
IMPLEMENTING MDAs:
SN | PROJECT DESCRIPTION | PROJECT CODE | PROJECT LOCATION LGA | NAME OF IMPLEMENTING COMPANY | DATE OF AWARD | CONTRACT SUM (Naira) | PROJECT STATISTIC/ PERFORMANCE (%) | EXPECTED DATE OF COMPLETION | RECOMMENDATION
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23

## Sheet2
IMPLEMENTING MDAs:
SN | PROJECT DESCRIPTION | PROJECT CODE | PROJECT LOCATION LGA | NAME OF IMPLEMENTING COMPANY | DATE OF AWARD | CONTRACT SUM (Naira) | PROJECT STATISTIC/ PERFORMANCE (%) | EXPECTED DATE OF COMPLETION | RECOMMENDATION
A | Education Sector
1 | Renovation of Government Day Secondary School (GDSS) Gulak |  | Gulak | UNDP |  | N/A
2 | Construction of perimeter fence at GDSS Gulak |  | Gulak | MRRR&HS |  | N/A
3 | Construction of 8 No. staff quarters (senior and junior) at GDSS Gulak |  | Gulak | MRRR&HS |  | N/A | 100% |  | COMPLETED
4 | Drilling of shallow aquifer borehole at GDSS Gulak staff quarters |  | Gulak | MRRR&HS |  | N/A | 100% |  | COMPLETED
B | Skills Development and Empowerment Sector
5 | Construction of gatehouse and perimeter fence at Shuwa Skill Acquisition Center |  | Shuwa | MRRR&HS SKILL TECH MANAGEMENT |  | N/A | 100% |  | COMPLETED
6 | Procurement and supply of 5KVA solar inverter at Shuwa Skill Acquisition Center |  | Shuwa | MRRR&HS |  | N/A | 100% |  | COMPLETED
7 | Procurement of training materials for Skill Acquisition Center, Shuwa |  | Shuwa | MRRR&HS |  | N/A | 100% |  | COMPLETED
8 | Training of 25 master trainers at Shuwa Skill Acquisition Center |  | Shuwa | PAWECA |  | N/A | 100% |  | COMPLETED
C | Security and Infrastructure Sector
9 | Procurement of 5KVA solar inverter and office equipment for the Ministry for RRR&HS |  | Head-Quater(Yola) | MRRR&HS |  | N/A | 100% |  | COMPLETED
10 | Training of 300 voluntary security outfits in Adamawa State |  | State-Wide | MRRR&HS,AHNI |  | N/A | 100% |  | COMPLETED
11 | Construction of police dormitory at Madagali |  | Madagali | MRRR&HS
12 | Construction of Civil Defence outpost at Madagali town |  | Madagali | MRRR&HS |  | N/A |  |  | ON-GOING
13 | Construction of junior staff quarters at Civil Defence office, Madagali |  | Madagali | MRRR&HS UNDP |  | N/A |  |  | NO-GOING
14 | Drilling of shallow aquifer borehole at Civil Defence office, Madagali town |  | Madagali | MRRR&HS |  | N/A |  |  | ON-GOING
15 | Construction of Civil Defence office at Gulak with senior and junior staff quarters |  | Gulak | MRRR&HS |  | N/A |  |  | ON-GOING
16 | Drilling of medium aquifer borehole at Civil Defence office, Gulak |  | Gulak | MRRR&HS
17 | Construction of 30 km anti-vehicular security ditch |  | Madagali | MRRR&HS UNDP | 19th oct, 2025 | N/A |  | 10th nov, 2025 | ON-GOING
D | Water, Sanitation and Hygiene (WASH) Sector
18 | Drilling of shallow aquifer borehole in Wagga |  | Wagga | MRRR&HS UNDP | 10th oct,2025 | 49554000 | 100% | 6th nov, 2025 | COMPLETED
19 | Drilling of shallow aquifer borehole in Sukur |  | Sukur | MRRR&HS UNDP | 25th sep, 2025 | 49554000 | 100% | 15th nov, 2025 | COMPLETED
20 | Drilling of shallow aquifer borehole in Madagali town |  | Madagali | MRRR&HS UNDP | 14th oct, 2025 | 49554000 | 100% | 8th nov, 2025 | COMPLETED
E | Livelihood and Economic Empowerment Sector
21 | Establishment of Women Village Loan and Savings Association (VLSA) at Gulak with 200 members |  | Gulak | MRRR&HS |  | N/A | 100% |  | COMPLETED
22 | Distribution of 250,000.00 each to 1,896 households severely affected by the 2024 flood in Numan, Demsa, Madagali, Michika and Lamurde. |  | Numan, Demsa, Madagali, Michika and Lamurde. | MRRR&HS/ADS Gov't |  | N/A | 100% |  | COMPLETED
F | Social Welfare and Psychosocial Support Sector
23 | Capacity building on mental health and psychosocial support for returnees and host communities in Madagali Local Government |  | Madagali | MRRR&HS | 2025-01-03 | N/A | 100% |  | COMPLETED
24 | Trained 300 members of volunteer security organizations (vso) |  | Yola North, Yola South,Madagali. | MRRR&HS, UNDP,AHNI |  |  |  | 19/12/2025
25 | Conduct Communal Clash Damage Assessment |  | Lamurde | Numan, Demsa, Madagali, Michika and Lamurde. | 2025-11-07 | N/A |  |  | ON-GOING
26 | State Government through MRRR&HS officiallly handed over the site to contractors for the commmencement of the phase ii implementation of reginal stabilization facility (RSF) project in Madagali. |  | Madagali | MRRR&HS | 22/10/2025 | N/A | 100% |  | COMPLETED
27 | Social impact project initiated the wife of the executive Governor, Hajiya Lami Ahmadu Umaru Fintiri in collaboration with international organizatin for migration (IOM) empower 200 vulnerable families across the state with business starter kits. |  | State-Wide | MRRR&HS IOM | 13/9/2025 | N/A | 100% |  | COMPLETED
28 | Conduct flood damage Assessment in Numan, Yola South & Hong. |  | Numan, Yola South, &Hong. | MRRR&HS,,NRC,MHUD,ASPC,HARAF, IOM,&RED CROSS | 2025-04-09 |  | 100% | 2025-08-09 | COMPLETED
| Disbursement of cash to flood victims in Yola south LGA and communal clash at Lamurde LGA |  | Yola south & Lamurde | MRRR&HS, ADSEMA& NRC |  |  |  |  | ON-GOING