## Sheet1
ADAMAWA STATE PLANNING COMMISSION
PROJECT MONITORING AND EVALUATION TEMPLATE 2024
IMPLEMENTING MDAs: MINISTRY OF HOUSING AND URBAN DEVELOPMENT
SN | PROJECT DESCRIPTION | PROJECT CODE | PROJECT LOCATION LGA | NAME OF IMPLEMENTING COMPANY | DATE OF AWARD | CONTRACT SUM (Naira) | CONTRACT SUM (Naira) | PROJECT STATISTIC/PERFORMANCE PERCENTAGE | EXPECTED DATE OF COMPLETION | RECOMMENDATION
1 | Construction of 2,000 Housing unit in various LGAs in the State |  | Malkohi, Yola South | Various Contractors | 2021 | 5,000,000,000.00 Rev 6,720,297,203.27 | 5795154878.27 | 76% | 12 Weeks
2 | Renovation of Deputy Governor Residence |  | Yola North | MESSRS Madugu Comm. & Constuction Ltd | 2022-12-01 | 81,983,796.78 Rev 130,711,542.19 Add-Wk 76,578,806.60 | 207290348.79 | 100% | 16 Months
3 | Construction, Furnishing and Consultancy of New Governor office complex |  | Yola North | MESSRS Madugu Comm. & Constuction Ltd | 2022-10-01 | 2,158,570,837.19 Rev 3,536,929,140.87 | 2580140617.84 | 79%
4 | Renovation and Furnishing of SSG office |  | Yola North | MESSRS Madugu Comm. & Constuction Ltd | 2023 | 104282203.73 | Nil
5 | Renovation and Furnishing of Head of Service office |  | Yola North | MESSRS Madugu Comm. & Constuction Ltd | 2023 | 70174805.23 | Nil
6 | Supply and Installation of street Light |  | Mubi | Uche Light Electrical Nigeria Ltd | 2016 | 354599925.94 | 305470778.27 | 100%
7 | Construction of New Warehouse at Government House |  | Yola North | MESSRS Madugu Comm. & Constuction Ltd | 2023-06-01 | 291,015,585.77 Add=wk 230,303,028.58 | 251379007.36 | 86% | 3 Months
8 | Consultancy on the construction of Government Lodge |  | Yola North | Metro Source Consultant Ltd | July 2015 Rev May 2017 | 44,057,577.88 Rev 70,891,753.28 | 40000000 | 100%
9 | Installation of Street Light along Girei Road Dougirei |  | Yola North | Uche Light Electrical Nigeria Ltd | 2017-10-01 | 145085579.58 | 76023644.3 | 100%
10 | Renovation of SSG Residence |  | Yola North | Innavison Nigeria Ltd | 2015-08-14 | 42650786.25 | 20000000 | 50%
11 | Establishment of Mobile Unit. Conversion of 2No Uncompleted Housing tooffice of 5No Block |  | Mubi | Hafai Nigeria Ltd | 2017-08-28 | 45140423.32 | 36166165.7 | 96%
12 | Renovation of Access Road and Landscaping work at Deputy Governor Office |  | Yola North | Yena Coswell Enterprise | 2015 | 29232275.25 | 12000000 | 60%
13 | Renovation and Furnishing of Gambo Lodge at Government House |  | Yola North | ADDA GORO Nigeria Ltd | 2015-10-11 | 25912348.44 | 20000000 | 95% | 12 Weeks
14 | Renovation and Furnishing of Commissioners Quarters |  | Yola North | MESSRS GHUMBU Global Nigeria Ltd | 2015-10-20 | 42600480.8 | Nil | 100%
15 | Ongoing Street Light project along Girei Street and link spanned 3.3KM |  | Yola North | Uche Light Electrical Nigeria Ltd | 2017-09-13 | 32188256.5 | Nil | 100%
16 | Renovation and Upgrade of Badminton and Tennis Court in Government House |  | Yola North | Reform Sport West African Ltd | 2022-11-01 | 131978360.84 | 52791344.34 | 40% | 12 Weeks
17 | Consultancy Service on the Construction of New Governors Office Complex |  | Yola North | Group One of Diventon Consultancy | 2022-06-01 | 166502217.73 | 132462020.31 | 79% | 16 Months