## Sheet1
ADAMAWA STATE PLANNING COMMISSION
PROJECT MONITORING AND EVALUATION TEMPLATE 2024
IMPLEMENTING MDAs: MINISTRY OF AGRICULTURE
SN | PROJECT DESCRIPTION | PROJECT CODE | PROJECT LOCATION LGA | NAME OF IMPLEMENTING COMPANY | DATE OF AWARD | CONTRACT SUM (Naira) | CONTRACT SUM (Naira) | PROJECT STATISTIC/PERFORMANCE PERCENTAGE | EXPECTED DATE OF COMPLETION | RECOMMENDATION
1 | Renovation and Reconstruction of Divisional Aricultural offices in eleven LGAs and construction of 10No of Stop-shops |  |  | Mubab Global Investment Nigeria Ltd | 2018-06-29 | 93037921.5 | 10000000 |  |  | Abandoned
2 | Renovation and Reconstruction of Divisional Aricultural offices in eleven LGAs and construction of 10No of Stop-shops |  |  | Amaimadel Integrated Service Nigeria | 2018-06-29 | 72156952.2 | 3000000 |  |  | Abandoned
3 | Renovation and Reconstruction of Divisional Aricultural offices in eleven LGAs and construction of 10No of Stop-shops |  |  | ABMUB Integrated Nigeria | 2018-06-29 | 144749039.1 | 15000000 |  |  | Abandoned
4 | Procurement of dry season farm inputs |  | 21 LGA | Kachalla Multi Links Ltd | 2024-03-28 | 454039200 | 181615680 |  |  | Ongoing