## Sheet1
ADAMAWA STATE PLANNING COMMISSION
PROJECT MONITORING AND EVALUATION TEMPLATE 2024
IMPLEMENTING MDAs: MINISTRY OF RURAL DEVELOPMENT
SN | PROJECT DESCRIPTION | PROJECT CODE | PROJECT LOCATION LGA | NAME OF IMPLEMENTING COMPANY | DATE OF AWARD | CONTRACT SUM (Naira) | PAYMENT TO CONTRACTOR | PROJECT STATISTIC/PERFORMANCE PERCENTAGE | EXPECTED DATE OF COMPLETION | RECOMMENDATION
1 | Electrification of Opalo, Shemun, Hoki and Zekun |  | Lamurde LGA | Bengin & Associate Ltd | 2023-01-16 | 243781700.09 | 195025360.08 | 80% | 2024-05-01
2 | Construction of Banjiram- Chikila 9.2 KM Road |  | Guyuk LGA | A.T Barak Service Ltd | 2022-12-30 | 247705968.13 | 198164756.5 | 85% | 2024-05-01
3 | Electrification of Bille, Kpasham Dong |  | Demsa LGA | Electromax Engr. Services Ltd | 2022-11-27 | 654630306.75 | 638254549.08 | 100% | 2024-04-01 | Awaiting Official Commissioning
4 | Electrification of So'o and Mapeo |  | Jada LGA | Electromax Engr. Services Ltd | 2022-11-27 | 270185099.25 | 256675844.9 | 85% | 2024-05-01
5 | Electrification of Humbutudi |  | Maiha LGA | Audu Gombi Investments Ltd | 2023-10-09 | 89398199.04 | 89398199.04 | 95% | 2024-05-01
6 | Electrification of Maiha-Gari |  | Maiha LGA | Ms Chale Nig Ltd | 2023-10-09 | 205205153.67 | 184684638.31 | 95% | 2024-05-01
7 | Electrification of Gorobo and Dapanti |  | Mayo-Belwa LGA | Mudaba Nig Ltd | 2023-10-09 | 155914940.71 | 140323446.28 | 90% | 2024-05-01
8 | Electrification of Fahar, Kaulewa, Mbewa and Wuyaku |  | Gombi LGA | Galaxy Rays Nig Ltd | 2023-10-09 | 192676258.1 | 154141007.28 | 100% | 2024-04-01 | Awaiting Official Commissioning
9 | Electricity Supply to Cottage Hospital Shelleng |  | Shelleng LGA | PRC Resources Ltd | 2023-12-12 | 34582200.7 | 34582200.7 | 15% | 2024-08-01
10 | Electricity Supply to Cottage Hospital Guyuk |  | Guyuk LGA | SWS Logistics | 2023-12-12 | 31106658.99 | 31106658.99 | 15% | 2024-08-01
11 | Electrification of Yolde Kohi |  | Yola South | Audu Gombi Investments Ltd | 2023-08-02 | 41623626.45 | 41623626.45 | 100% | 2024-04-01 | Awaiting Official Commissioning
12 | Electrification of Hosere Bembee |  | Yola South | Audu Gombi Investments Ltd | 2023-08-02 | 45927250.75 | 45927250.75 | 100% | 2024-04-01 | Awaiting Official Commissioning